SANJIVANI UNIVERSITY

UNIT-2 AGILE MINI-PROJECT

SU-DevOps

University DevOps Project & Deployment Management Platform

| Item | Details |
| --- | --- |
| Project Type | Agile Software Development / DevOps Management Platform |
| Primary Users | Students, Faculty Mentors, Project Teams, Department Administrators |
| Student Name | Shriraj Kamble |
| PRN | 2125UMLM1030 |
| Student Name | Prathamesh Kolhe |
| PRN | 2125UMLM1059 |
| Recommended Framework | Scrum |
| Planned Release | MVP Release 1.0 |
| Report Scope | Complete Unit-2 Agile Project Planning and Documentation |

Prepared as a complete model project based on the provided Unit-2 Agile Mini-Project requirements.

# Contents

1. Executive Summary

2. Business Problem and Product Discovery

3. Agile Product Vision

4. Stakeholders and Personas

5. Product Scope, MVP and Success Criteria

6. Scrum Team Structure and Responsibilities

7. System Concept and High-Level Architecture

8. Project Epics

9. User Story Repository

10. Acceptance Criteria and Definition of Done

11. Prioritized Product Backlog

12. Story Point Estimation

13. Release Roadmap and Project Timeline

14. Sprint Planning and Sprint Backlogs

15. Scrum Board

16. Burndown Chart

17. Scrum Ceremonies

18. Sprint Reviews

19. Sprint Retrospective

20. Agile Framework Comparison

21. DevOps Delivery Flow and Quality Gates

22. Risks, Constraints and Mitigation

23. Project Metrics and Success Dashboard

24. Final Deliverables Checklist

25. Conclusion

# 1. Executive Summary

SU-DevOps is a proposed web-based university platform that brings common software delivery activities into a single project workspace. It is designed for student development teams and their mentors to organize projects, connect code repositories, track issues, automate build/test activity, manage deployments, monitor delivery status, and generate project reports.

The project follows the Agile structure specified in the provided Unit-2 mini-project brief. The report translates a software product idea into an Agile Product Vision, Scrum team structure, Epics, User Stories, Acceptance Criteria, Product Backlog, Story Point estimates, Sprint Plans, Scrum Board, Burndown Chart, Scrum Reviews, Retrospective, Agile Framework Comparison, and Release Roadmap. The source brief explicitly identifies these deliverables as the expected Unit-2 outputs.

For this model project, Scrum is selected as the primary framework because the product has a manageable scope, a defined team structure, and a need for short iterative delivery cycles. The MVP focuses on authentication, project setup, repository integration, issue tracking, basic CI/CD visibility, deployment records, notifications, and reporting.

# 2. Business Problem and Product Discovery

The Unit-2 brief begins by asking students to review the Product Discovery material, stakeholders, business requirements, functional and non-functional requirements, personas, MVP, and roadmap before translating the product into Agile deliverables.  For SU-DevOps, these discovery elements are consolidated into the following working problem statement.

## 2.1 Problem Statement

University software teams often manage code, tasks, builds, testing, deployment records, and project evidence across separate tools. This makes it difficult for students and mentors to see the complete development lifecycle in one place, understand current project health, and maintain consistent delivery evidence for academic evaluation.

## 2.2 Proposed Solution

SU-DevOps provides one project workspace where a team can create a project, connect a Git repository, manage tasks and issues, view pipeline results, record deployments, receive notifications, and generate a consolidated delivery report.

## 2.3 Business Requirements

Enable authenticated project workspaces for university users.

Allow teams to create and manage software projects.

Connect a repository and show repository activity relevant to the project.

Provide task and issue tracking with status and priority.

Provide visibility of build/test pipeline results.

Maintain deployment history and release status.

Provide notifications for important project events.

Generate reports for project progress and delivery evidence.

Maintain role-based access to student, mentor, and administrator actions.

## 2.4 Non-Functional Requirements

Security: authenticated access and role-based authorization.

Usability: simple dashboard and clear workflow states.

Performance: common dashboard operations should respond promptly under normal academic load.

Availability: core project information should remain accessible during project reviews.

Maintainability: modular services and documented interfaces.

Testability: automated validation for critical project workflows.

Scalability: architecture should support multiple project teams and repositories.

# 3. Agile Product Vision

The provided Unit-2 document defines Product Vision work around overall product objective, primary users, business benefits, measurable success criteria, constraints, and expected capabilities.

Product Vision: Develop a secure and user-friendly university DevOps platform that enables student teams and mentors to manage software projects, source code integration, delivery pipelines, deployments, issues, notifications, and reporting through a single web-based workspace.

## 3.1 Product Objective

Create a centralized academic software delivery environment that makes the software lifecycle visible, repeatable, and measurable for project teams.

## 3.2 Business Benefits

Improves transparency of project progress for students and mentors.

Reduces fragmentation between coding, issue tracking, pipeline monitoring, and deployment evidence.

Encourages repeatable DevOps practices in academic projects.

Provides structured evidence for demonstrations and project reviews.

Creates a foundation for future automation and analytics.

## 3.3 Measurable Success Criteria

| Metric | Target for MVP |
| --- | --- |
| User onboarding success | At least 90% of pilot users can complete registration/login without assistance |
| Project setup | A team can create and configure a project in under 5 minutes |
| Repository connection | Repository configuration is saved and visible on the project dashboard |
| Pipeline visibility | Latest build/test status is visible for connected projects |
| Deployment traceability | Every recorded deployment has status, timestamp, and environment |
| Reporting | Project summary report can be generated from stored project data |
| Usability | Pilot feedback average of at least 4/5 for dashboard clarity |

## 3.4 Project Constraints

Limited student development time and fixed academic milestones.

Free or institutionally available infrastructure may be preferred for the MVP.

Third-party API availability can affect repository and pipeline integration.

Team members may have different levels of DevOps experience.

The first release should prioritize core academic value over advanced enterprise features.

# 4. Stakeholders and Personas

| Stakeholder | Interest | Influence | Primary Needs |
| --- | --- | --- | --- |
| Student Developer | High | High | Project workspace, tasks, repository, pipeline and deployment visibility |
| Faculty Mentor | High | High | Progress monitoring, review feedback, project reports |
| Department Administrator | Medium | High | User/project oversight and reporting |
| Project Team Lead | High | Medium | Planning, assignment, delivery status and blockers |
| External Evaluator | Medium | Low | Clear project evidence and final report |
| Platform Administrator | Medium | High | Security, access control, service health |

## 4.1 Student Developer Persona

Goal: build and submit a software project using modern development practices. Pain points: scattered project information, unclear task ownership, manual evidence collection. Expected value: one dashboard for coding, tasks, pipelines, deployments, and project status.

## 4.2 Faculty Mentor Persona

Goal: understand whether a team is progressing and whether the project follows disciplined development practices. Pain points: limited visibility between reviews. Expected value: project health summary, activity history, release status, and evidence reports.

# 5. Product Scope, MVP and Success Criteria

## 5.1 In Scope for MVP

User registration, login, logout, and role-based access.

Project creation and project member management.

Repository connection details and repository status.

Issue/task creation, assignment, priority, and workflow status.

CI/CD pipeline status display and execution history.

Deployment record creation and status tracking.

Project notifications.

Basic project, activity, and delivery reports.

## 5.2 Out of Scope for MVP

Fully managed cloud infrastructure provisioning.

Advanced AI code review and autonomous remediation.

Enterprise-scale multi-tenant billing.

Complex Kubernetes cluster orchestration.

Native mobile application.

## 5.3 Definition of MVP Done

The MVP is considered complete when all high-priority backlog items have met their Acceptance Criteria, critical defects are resolved or explicitly accepted, core flows pass testing, and the team can demonstrate a complete journey from project creation through task tracking, pipeline visibility, deployment recording, and reporting.

# 6. Scrum Team Structure and Responsibilities

The Unit-2 brief requires Scrum Teams to assign Product Owner, Scrum Master, and Development Team responsibilities.

| Role | Primary Responsibility | SU-DevOps Responsibilities |
| --- | --- | --- |
| Product Owner | Owns product value and backlog priority | Defines requirements, orders backlog, represents student/mentor needs, accepts completed work |
| Scrum Master | Facilitates Scrum and removes impediments | Facilitates planning, daily Scrum, review and retrospective; tracks blockers; protects Agile process |
| UI/UX Developer | Builds usable interface | Dashboard, project screens, task views, responsive UI |
| Backend Developer | Implements application services | Authentication, project APIs, task APIs, deployment records, reporting APIs |
| DevOps/Integration Engineer | Builds delivery automation | Repository integration, pipeline status, deployment workflow, environment configuration |
| QA/Documentation Engineer | Validates quality and evidence | Test cases, acceptance validation, defect tracking, user guide and review evidence |

# 7. System Concept and High-Level Architecture

The following architecture is a project design proposed for this model. It keeps the user-facing application separate from repository, pipeline, deployment, and reporting integrations so that each capability can evolve independently.

| Layer | Components | Purpose |
| --- | --- | --- |
| Presentation | Web dashboard, project workspace, reports | User interaction and visualization |
| Application | Authentication service, project service, task service, reporting service | Business logic and API operations |
| Integration | Repository connector, CI/CD connector, deployment connector, notification service | Communication with external delivery tools |
| Data | Relational database, audit/activity log | Persist users, projects, issues, pipeline results and deployment records |
| Quality & Security | Validation, authorization, logging, automated tests | Protect data and maintain release quality |

## 7.1 Main User Flow

User signs in and opens the project dashboard.

Team creates a project and assigns members.

Project connects to a source repository.

Team creates tasks and tracks progress on the Scrum board.

Code changes trigger or are reflected through a CI/CD pipeline integration.

Team views build/test status and addresses failures.

A deployment is recorded with environment and release status.

Team and mentor review progress and generate a project report.

# 8. Project Epics

The Unit-2 brief asks students to organize the complete application into high-level functional modules called Epics.  For SU-DevOps, the Epics are defined below.

| Epic ID | Epic | Scope |
| --- | --- | --- |
| E1 | Authentication & Security | Secure account access, roles and session management. |
| E2 | Project Management | Create projects, teams, members and project settings. |
| E3 | Repository Management | Connect source repositories and display repository information. |
| E4 | Issue & Task Tracking | Create, assign, prioritize and track work items. |
| E5 | CI/CD Pipeline Management | View and manage build/test workflow status. |
| E6 | Deployment Management | Record releases, environments and deployment status. |
| E7 | Notifications | Notify users about tasks, pipeline failures, reviews and releases. |
| E8 | Reporting & Analytics | Generate project progress, delivery and activity reports. |

# 9. User Story Repository

The Unit-2 brief requires User Stories in Agile format and states that every identified feature should be represented through stories.

| ID | Epic | User Story | Priority | SP |
| --- | --- | --- | --- | --- |
| US-01 | E1 | As a user, I want to register an account so that I can access SU-DevOps. | High | 3 |
| US-02 | E1 | As a registered user, I want to log in securely so that my project data remains protected. | High | 3 |
| US-03 | E1 | As an administrator, I want to assign roles so that users receive appropriate permissions. | High | 5 |
| US-04 | E2 | As a team lead, I want to create a project so that my team has a shared workspace. | High | 3 |
| US-05 | E2 | As a team lead, I want to add/remove members so that project access is controlled. | High | 3 |
| US-06 | E3 | As a developer, I want to connect a repository so that project code activity is associated with the project. | High | 5 |
| US-07 | E3 | As a user, I want to view repository status so that I know whether the integration is active. | Medium | 3 |
| US-08 | E4 | As a developer, I want to create a task so that project work can be tracked. | High | 3 |
| US-09 | E4 | As a team lead, I want to assign and prioritize tasks so that work is organized. | High | 5 |
| US-10 | E4 | As a developer, I want to update task status so that progress remains visible. | High | 3 |
| US-11 | E5 | As a developer, I want to view the latest CI build result so that I know whether changes passed validation. | High | 5 |
| US-12 | E5 | As a team lead, I want to view pipeline history so that recurring delivery issues can be identified. | Medium | 5 |
| US-13 | E6 | As a developer, I want to record a deployment so that releases are traceable. | High | 5 |
| US-14 | E6 | As a mentor, I want to see deployment status by environment so that release readiness is visible. | Medium | 5 |
| US-15 | E7 | As a user, I want notifications for important project events so that I do not miss blockers. | Medium | 3 |
| US-16 | E8 | As a mentor, I want a project progress report so that I can review project health. | Medium | 5 |
| US-17 | E8 | As an administrator, I want project activity summaries so that I can monitor multiple teams. | Low | 8 |
| US-18 | E2 | As a project member, I want a dashboard showing current project status so that I can understand work at a glance. | Medium | 5 |
| US-19 | E5 | As a team lead, I want failed pipeline status highlighted so that failures are addressed quickly. | Medium | 3 |
| US-20 | E8 | As a team, I want a release report so that project demonstrations have clear evidence. | Low | 5 |

# 10. Acceptance Criteria and Definition of Done

The Unit-2 brief describes Acceptance Criteria as measurable conditions that determine whether a User Story is complete and gives examples such as successful login, appropriate error handling, redirection, and session management.

| Story | Acceptance Criteria |
| --- | --- |
| US-01 Registration | Registration page loads; required fields are validated; unique account is created; duplicate email is rejected; success confirmation shown. |
| US-02 Login | Registered user can log in; invalid credentials show an error; successful login reaches dashboard; session is maintained securely. |
| US-04 Create Project | Authorized team lead can create project; project name is required; project appears in dashboard; creator becomes project member. |
| US-06 Connect Repository | Authorized user can save repository details; connection status is shown; invalid configuration is rejected with clear feedback. |
| US-08 Create Task | User can create task with title and priority; task is stored; task appears in project board; default workflow status is applied. |
| US-11 Pipeline Status | Latest pipeline run is displayed; pass/fail state is visible; timestamp is shown; failed state is understandable. |
| US-13 Deployment Record | Deployment includes environment, version/reference, timestamp and status; history is retained; unauthorized users cannot modify it. |
| US-16 Progress Report | Report includes project summary, task progress, pipeline status, deployment history and date; report can be viewed or exported. |

## 10.1 Definition of Done

Code is implemented and reviewed by another team member.

Acceptance Criteria are fully met.

Unit/integration tests relevant to the story pass.

No unresolved Critical/High defect blocks the story.

UI and API behavior are documented where applicable.

Demonstration is possible in the agreed environment.

Product Owner accepts the story.

# 11. Prioritized Product Backlog

The source brief says backlog priority should consider business value, user importance, technical dependencies, and implementation complexity.

| ID | Epic | Priority | User Story | SP | Value |
| --- | --- | --- | --- | --- | --- |
| US-01 | E1 | High | As a user, I want to register an account so that I can access SU-DevOps. | 3 | Must-have MVP |
| US-02 | E1 | High | As a registered user, I want to log in securely so that my project data remains protected. | 3 | Must-have MVP |
| US-03 | E1 | High | As an administrator, I want to assign roles so that users receive appropriate permissions. | 5 | Must-have MVP |
| US-04 | E2 | High | As a team lead, I want to create a project so that my team has a shared workspace. | 3 | Must-have MVP |
| US-05 | E2 | High | As a team lead, I want to add/remove members so that project access is controlled. | 3 | Must-have MVP |
| US-06 | E3 | High | As a developer, I want to connect a repository so that project code activity is associated with the project. | 5 | Must-have MVP |
| US-07 | E3 | Medium | As a user, I want to view repository status so that I know whether the integration is active. | 3 | Important enhancement |
| US-08 | E4 | High | As a developer, I want to create a task so that project work can be tracked. | 3 | Must-have MVP |
| US-09 | E4 | High | As a team lead, I want to assign and prioritize tasks so that work is organized. | 5 | Must-have MVP |
| US-10 | E4 | High | As a developer, I want to update task status so that progress remains visible. | 3 | Must-have MVP |
| US-11 | E5 | High | As a developer, I want to view the latest CI build result so that I know whether changes passed validation. | 5 | Must-have MVP |
| US-12 | E5 | Medium | As a team lead, I want to view pipeline history so that recurring delivery issues can be identified. | 5 | Important enhancement |
| US-13 | E6 | High | As a developer, I want to record a deployment so that releases are traceable. | 5 | Must-have MVP |
| US-14 | E6 | Medium | As a mentor, I want to see deployment status by environment so that release readiness is visible. | 5 | Important enhancement |
| US-15 | E7 | Medium | As a user, I want notifications for important project events so that I do not miss blockers. | 3 | Important enhancement |
| US-16 | E8 | Medium | As a mentor, I want a project progress report so that I can review project health. | 5 | Important enhancement |
| US-17 | E8 | Low | As an administrator, I want project activity summaries so that I can monitor multiple teams. | 8 | Later / scale-up |
| US-18 | E2 | Medium | As a project member, I want a dashboard showing current project status so that I can understand work at a glance. | 5 | Important enhancement |
| US-19 | E5 | Medium | As a team lead, I want failed pipeline status highlighted so that failures are addressed quickly. | 3 | Important enhancement |
| US-20 | E8 | Low | As a team, I want a release report so that project demonstrations have clear evidence. | 5 | Later / scale-up |

# 12. Story Point Estimation

The Unit-2 brief specifies the example scale: 1 = Very Easy, 2 = Easy, 3 = Moderate, 5 = Difficult, 8 = Very Difficult, and 13 = Highly Complex.

| Story Points | Interpretation | SU-DevOps Example |
| --- | --- | --- |
| 1 | Very Easy | Minor text or display adjustment |
| 2 | Easy | Simple validation or small UI behavior |
| 3 | Moderate | Login screen, simple task CRUD, basic dashboard widget |
| 5 | Difficult | Repository integration, pipeline status, deployment record |
| 8 | Very Difficult | Cross-module reporting or multi-system integration |
| 13 | Highly Complex | Potential future enterprise automation / large architectural change |

## 12.1 Estimation Method

The team conducts Planning Poker: each member independently selects a Story Point value, differences are discussed, assumptions are clarified, and the team agrees on one final estimate. This supports shared understanding rather than estimating by one person only.

## 12.2 Current MVP Estimate

Total estimated backlog size for the 20 modeled stories: 85 Story Points. The Sprint Plan below allocates the highest-value work first and leaves lower-priority analytics work for later delivery.

# 13. Release Roadmap and Project Timeline

| Stage | Schedule | Focus | Key Deliverable |
| --- | --- | --- | --- |
| Phase 1 | Week 1 | Discovery & setup | Vision, backlog baseline, repository, project skeleton |
| Sprint 1 | Weeks 2-3 | Foundation | Authentication, roles, project setup |
| Sprint 2 | Weeks 4-5 | Collaboration | Repository connection, tasks, project dashboard |
| Sprint 3 | Weeks 6-7 | Delivery | CI/CD status and deployment tracking |
| Sprint 4 | Weeks 8-9 | Visibility | Notifications, reporting and polish |
| Release 1.0 | Week 10 | MVP release | System demo, acceptance, documentation |

# 14. Sprint Planning and Sprint Backlogs

The source brief expects multiple development Sprints with a Sprint Goal, Sprint Backlog and expected deliverables.

| Sprint | Goal | Stories | Planned SP | Deliverable |
| --- | --- | --- | --- | --- |
| Sprint 1 | Foundation & Secure Access | ['US-01', 'US-02', 'US-03', 'US-04', 'US-05'] | 19 | Working authentication, roles and project creation |
| Sprint 2 | Team Collaboration | ['US-06', 'US-07', 'US-08', 'US-09', 'US-10', 'US-18'] | 24 | Repository and task workflow with dashboard |
| Sprint 3 | Continuous Delivery | ['US-11', 'US-12', 'US-13', 'US-14', 'US-19'] | 23 | Pipeline visibility and deployment tracking |
| Sprint 4 | Communication & Reporting | ['US-15', 'US-16', 'US-17', 'US-20'] | 21 | Notifications, reports and MVP polish |

## Sprint 1 Detailed Plan

| ID | Story | Priority | SP | Initial Status |
| --- | --- | --- | --- | --- |
| US-01 | As a user, I want to register an account so that I can access SU-DevOps. | High | 3 | To Do |
| US-02 | As a registered user, I want to log in securely so that my project data remains protected. | High | 3 | To Do |
| US-03 | As an administrator, I want to assign roles so that users receive appropriate permissions. | High | 5 | To Do |
| US-04 | As a team lead, I want to create a project so that my team has a shared workspace. | High | 3 | To Do |
| US-05 | As a team lead, I want to add/remove members so that project access is controlled. | High | 3 | To Do |

Sprint Goal: Foundation & Secure Access

Sprint Deliverable: Working authentication, roles and project creation

Sprint Exit Condition: All selected stories meet Acceptance Criteria and Definition of Done, and the team can demonstrate the integrated increment.

## Sprint 2 Detailed Plan

| ID | Story | Priority | SP | Initial Status |
| --- | --- | --- | --- | --- |
| US-06 | As a developer, I want to connect a repository so that project code activity is associated with the project. | High | 5 | To Do |
| US-07 | As a user, I want to view repository status so that I know whether the integration is active. | Medium | 3 | To Do |
| US-08 | As a developer, I want to create a task so that project work can be tracked. | High | 3 | To Do |
| US-09 | As a team lead, I want to assign and prioritize tasks so that work is organized. | High | 5 | To Do |
| US-10 | As a developer, I want to update task status so that progress remains visible. | High | 3 | To Do |
| US-18 | As a project member, I want a dashboard showing current project status so that I can understand work at a glance. | Medium | 5 | To Do |

Sprint Goal: Team Collaboration

Sprint Deliverable: Repository and task workflow with dashboard

Sprint Exit Condition: All selected stories meet Acceptance Criteria and Definition of Done, and the team can demonstrate the integrated increment.

## Sprint 3 Detailed Plan

| ID | Story | Priority | SP | Initial Status |
| --- | --- | --- | --- | --- |
| US-11 | As a developer, I want to view the latest CI build result so that I know whether changes passed validation. | High | 5 | To Do |
| US-12 | As a team lead, I want to view pipeline history so that recurring delivery issues can be identified. | Medium | 5 | To Do |
| US-13 | As a developer, I want to record a deployment so that releases are traceable. | High | 5 | To Do |
| US-14 | As a mentor, I want to see deployment status by environment so that release readiness is visible. | Medium | 5 | To Do |
| US-19 | As a team lead, I want failed pipeline status highlighted so that failures are addressed quickly. | Medium | 3 | To Do |

Sprint Goal: Continuous Delivery

Sprint Deliverable: Pipeline visibility and deployment tracking

Sprint Exit Condition: All selected stories meet Acceptance Criteria and Definition of Done, and the team can demonstrate the integrated increment.

## Sprint 4 Detailed Plan

| ID | Story | Priority | SP | Initial Status |
| --- | --- | --- | --- | --- |
| US-15 | As a user, I want notifications for important project events so that I do not miss blockers. | Medium | 3 | To Do |
| US-16 | As a mentor, I want a project progress report so that I can review project health. | Medium | 5 | To Do |
| US-17 | As an administrator, I want project activity summaries so that I can monitor multiple teams. | Low | 8 | To Do |
| US-20 | As a team, I want a release report so that project demonstrations have clear evidence. | Low | 5 | To Do |

Sprint Goal: Communication & Reporting

Sprint Deliverable: Notifications, reports and MVP polish

Sprint Exit Condition: All selected stories meet Acceptance Criteria and Definition of Done, and the team can demonstrate the integrated increment.

# 15. Scrum Board

The Unit-2 brief presents a typical board flow of Backlog, To Do, In Progress, Testing and Completed, with the board updated during Sprint execution.

| Column | Story | Card Description |
| --- | --- | --- |
| Backlog | US-17 | Admin analytics |
| To Do | US-15 | Notifications |
| To Do | US-16 | Progress report |
| In Progress | US-11 | Pipeline status |
| In Progress | US-13 | Deployment record |
| Testing | US-12 | Pipeline history |
| Testing | US-14 | Deployment by environment |
| Completed | US-01 | Registration |
| Completed | US-02 | Login |
| Completed | US-04 | Create project |
| Completed | US-08 | Create task |
| Completed | US-10 | Task status update |

Board policy: a work item moves to Testing only after implementation is complete; it moves to Completed only after test evidence and Acceptance Criteria are satisfied. Blocked items remain visible with a blocker note rather than being silently hidden.

# 16. Burndown Chart

The burndown below is a modeled project-management artifact for the four-sprint plan. It illustrates how remaining Story Points can be tracked against an ideal trend. Actual values are illustrative planning data, not measurements from an executed software release.

Interpretation: A healthy burn-down generally trends downward toward zero. A long plateau indicates blockers or under-estimation and should trigger discussion during Daily Scrum, Sprint Review or Retrospective.

# 17. Scrum Ceremonies

The Unit-2 brief asks teams to simulate Sprint Planning, Daily Scrum, Sprint Review and Sprint Retrospective.

| Ceremony | Purpose | SU-DevOps Practice | Output |
| --- | --- | --- | --- |
| Sprint Planning | Select stories and define the Sprint Goal | Review ordered backlog, check capacity, identify dependencies | Sprint Goal + Sprint Backlog |
| Daily Scrum | Synchronize team progress | Each member states yesterday, today, blockers | Updated board + blocker list |
| Sprint Review | Demonstrate increment and gather feedback | Live demo to Product Owner and mentor | Accepted stories + feedback |
| Sprint Retrospective | Improve team process | Discuss what went well, challenges, improvements | Action items for next Sprint |

## 17.1 Daily Scrum Prompts

What did I complete yesterday?

What will I work on today?

What challenge or blocker am I facing?

# 18. Sprint Reviews

| Sprint | Demo | Review Outcome | Action |
| --- | --- | --- | --- |
| Sprint 1 | Demo login, role access and project creation | Authentication accepted; minor UI polish feedback | Improve error message consistency |
| Sprint 2 | Demo repository connection, task workflow and dashboard | Collaboration flow accepted | Add clearer repository sync state |
| Sprint 3 | Demo pipeline results and deployment history | Delivery traceability accepted | Improve failed-pipeline visibility |
| Sprint 4 | Demo notifications, reports and release evidence | MVP release scope accepted | Document post-MVP enhancement backlog |

# 19. Sprint Retrospective

| Sprint | What Went Well | Challenge | Improvement |
| --- | --- | --- | --- |
| Sprint 1 | Clear role split; setup was fast | Permission assumptions created rework | Write role matrix before implementation |
| Sprint 2 | Task workflow improved visibility | Repository integration dependency caused delays | Mock external responses early |
| Sprint 3 | Pipeline status gave strong demo value | Test coverage lagged implementation | Reserve explicit QA capacity each Sprint |
| Sprint 4 | Reporting consolidated evidence effectively | Last-minute polish compressed documentation time | Freeze core scope earlier and document continuously |

Retrospective rule: each Sprint should end with at least one concrete process improvement that can be observed in the next Sprint. This keeps the retrospective action-oriented rather than purely descriptive.

# 20. Agile Framework Comparison

The Unit-2 brief specifically asks students to compare Scrum, Kanban, Extreme Programming (XP), Lean Development, Large Scale Scrum (LeSS), Scaled Agile Framework (SAFe), and Scrum@Scale, and then recommend a suitable framework for the project.

| Framework | Core Idea | Fit for SU-DevOps | Decision |
| --- | --- | --- | --- |
| Scrum | Time-boxed Sprints, defined roles, events and backlog | Excellent for a student team with regular academic milestones | Recommended |
| Kanban | Continuous flow and work-in-progress limits | Useful for support/maintenance after MVP | Secondary |
| XP | Engineering discipline, pair programming, TDD, CI | Strong engineering practices but more process than needed for the academic product plan | Adopt selected practices |
| Lean | Waste reduction and value focus | Helpful mindset for prioritization | Supporting principle |
| LeSS | Scaling Scrum across multiple teams | Not necessary for a small student team | Not selected |
| SAFe | Large-scale portfolio/program coordination | Too heavy for the project size | Not selected |
| Scrum@Scale | Scaling Scrum networks | Useful only if the product grows into multiple Scrum teams | Future option |

Recommendation: Use Scrum as the primary Agile framework, supplemented by selected XP/DevOps engineering practices such as automated testing, continuous integration, code review and small-batch changes.

# 21. DevOps Delivery Flow and Quality Gates

SU-DevOps is itself a DevOps-oriented product, so the project plan incorporates a simple delivery flow aligned with the Sprint lifecycle.

| Stage | Activities | Quality Gate |
| --- | --- | --- |
| Plan | Refine stories, acceptance criteria, dependencies | Story is ready and measurable |
| Develop | Implement code, review changes | Peer review complete |
| Build | Compile/package application | Build succeeds |
| Test | Run unit/integration/UI checks | Critical tests pass |
| Release | Prepare release candidate | Acceptance Criteria satisfied |
| Deploy | Deploy to target environment | Deployment recorded and smoke test passes |
| Monitor | Observe status, logs and failures | Known issues captured and assigned |
| Improve | Review metrics and feedback | Retrospective action selected |

## 21.1 Suggested Technology Direction

Frontend: responsive web interface using a component-based UI approach.

Backend: REST-style application service layer.

Database: relational data store for users, projects, tasks and delivery records.

Source Control: Git-based repository integration.

CI/CD: pipeline system that reports build/test status.

Deployment: environment-aware deployment records and release history.

Quality: automated tests, code review, logging and acceptance validation.

Technology note: These technology choices are project design recommendations for the SU-DevOps model and are not specified by the uploaded Unit-2 source document.

# 22. Risks, Constraints and Mitigation

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Third-party repository/API instability | Medium | High | Use adapter layer, retries and mock test data |
| R2 | Pipeline integration complexity | High | High | Start with read-only status integration, add control actions later |
| R3 | Limited student time | High | High | Prioritize MVP, maintain WIP limits, review backlog weekly |
| R4 | Security misconfiguration | Medium | High | Role matrix, validation, secure session handling, access tests |
| R5 | Incomplete test coverage | Medium | High | Reserve QA capacity in every Sprint; automate regression tests |
| R6 | Scope creep | High | Medium | Product Owner controls backlog; defer non-MVP items |
| R7 | Poor documentation at release time | Medium | Medium | Maintain documentation as part of Definition of Done |

# 23. Project Metrics and Success Dashboard

| Metric | Definition | Use |
| --- | --- | --- |
| Sprint Velocity | Story Points completed per Sprint | Use trend across Sprints; avoid comparing teams solely by velocity |
| Sprint Burndown | Remaining work over time | Detect blockers and scope pressure |
| Defect Count | Open defects by severity | Track quality and release readiness |
| Build Success Rate | Successful pipeline runs / total runs | Measure delivery stability |
| Deployment Success Rate | Successful deployments / total deployments | Measure release reliability |
| Lead Time | Time from selected story to completed story | Identify delivery delays |
| Blocked Time | Time spent blocked | Identify dependencies and process issues |
| Review Acceptance | Accepted vs rejected Sprint stories | Measure readiness and Product Owner satisfaction |

## 23.1 Example Release Dashboard

| Indicator | Target | Example MVP Status |
| --- | --- | --- |
| MVP backlog completion | 100% of committed High-priority stories | Target: 100% |
| Critical defects at release | 0 | Target: 0 |
| High-severity unresolved defects | 0 unless explicitly accepted | Target: 0 |
| Pipeline visibility | Available for connected projects | Target: Yes |
| Deployment traceability | All release records auditable | Target: Yes |
| Project report generation | Working for MVP scope | Target: Yes |

# 24. Final Deliverables Checklist

The checklist below maps the project outputs to the deliverables explicitly listed in the Unit-2 brief.

| Required Deliverable | Status in This Report |
| --- | --- |
| Agile Project Planning Report | Included |
| Product Vision Document | Included |
| Scrum Team Structure | Included |
| Scrum Roles and Responsibilities Document | Included |
| Epic Documentation | Included |
| User Story Repository | Included |
| Acceptance Criteria Document | Included |
| Prioritized Product Backlog | Included |
| Story Point Estimation Sheet | Included |
| Sprint Planning Document | Included |
| Sprint Backlog | Included |
| Scrum Board | Included |
| Burndown Chart | Included |
| Sprint Review Report | Included |
| Sprint Retrospective Report | Included |
| Agile Framework Comparison Report | Included |
| Project Timeline and Release Roadmap | Included |
| Complete Agile Documentation | Included |

# 25. Conclusion

SU-DevOps converts a university software-delivery problem into a structured Agile product with a clear Product Vision, stakeholder focus, prioritized backlog, measurable Acceptance Criteria, Sprint-based delivery, Scrum governance, and a DevOps-oriented quality flow. The MVP is intentionally limited to capabilities that support project creation, collaboration, delivery visibility, deployment traceability and reporting.

The project can be used as the base submission for the Unit-2 Agile Mini-Project and can also serve as the planning blueprint for an actual implementation. The highest-value next step after the planning stage is to build Sprint 1, validate the core user journey, and use real Sprint evidence to update the illustrative metrics in this report.

Source basis: This report is structured from the uploaded Unit-2 Agile Mini-Project document. Where SU-DevOps-specific details were needed, they are clearly presented as a proposed project design rather than as facts from the source.